## Action Log
Ransomware Exercise - Timeline and Action Log
Time | Inject / Event | Owner | Decision Required | Action Taken | Status | Evidence / Notes | Next Step
08:15 | Employee reports encrypted files and ransom note | Service Desk | Escalate severity? | Opened security incident and isolated endpoint | Closed | Case ticket created; endpoint disconnected from network | Notify security operations lead
08:40 | Shared drives inaccessible | Security Operations | Containment scope? | Disabled affected user accounts and blocked suspicious indicators | In Progress | Potential lateral movement under review | Assess backup integrity and spread
09:00 | Customer support reports portal impact | Incident Commander | Executive notification? | Sent initial leadership update with known facts | Closed | Business impact emerging | Prepare customer-facing holding statement
10:00 | Threat actor claims data exfiltration | Legal / Privacy | Regulatory exposure? | Initiated legal review and data exposure analysis | In Progress | Need forensic validation | Coordinate decision on breach notification obligations

## Roles
Exercise Roles and Responsibilities
Role | Primary Responsibility | Backup Contact | Decision Authority
Incident Commander | Coordinates response, priorities, and executive updates | Deputy IC | Overall response direction
Security Operations Lead | Drives containment and investigation | SOC Manager | Technical containment actions
IT Operations Lead | Supports infrastructure isolation and recovery | Systems Manager | Endpoint and server recovery execution
Legal / Privacy | Assesses notification and regulatory obligations | Privacy Counsel | External notification and legal strategy
Communications Lead | Prepares internal and external messaging | Corporate Affairs | Approved communications release