## Readiness Tracker
SOC 2 Readiness Assessment
Criterion | Control Area | Current Status | Evidence Available | Gap Rating (1-3) | Priority | Remediation Action | Owner
CC6.1 | Logical access and MFA | Partially Implemented | Some screenshots, not complete | 3 | Critical | Enforce MFA for all workforce and admin identities | IT Security Lead
CC6.2 | User access reviews | Partially Implemented | Manual review records only | 2 | High | Formalize quarterly review workflow and evidence retention | GRC Analyst
CC7.2 | Change management | Partially Implemented | Ticket approvals inconsistent | 2 | High | Require documented approvals and rollback considerations for production changes | Engineering Manager
CC7.3 | Monitoring | Planned | Limited alert records | 3 | High | Define alert use cases and retain investigation records | Security Operations Lead
A1.2 | Availability and recovery | Partially Implemented | Backups exist, test evidence limited | 2 | Medium | Schedule and document recurring restoration tests | Infrastructure Lead
CC1.2 | Governance and control ownership | Implemented | Control owner list available | 1 | Medium | Maintain annual review of control ownership | Compliance Manager

## Dashboard
Readiness Dashboard
Status | Count | % of Total | Metric | Value
Implemented | 1 | 16.67% | Open Critical / High | 4
Partially Implemented | 4 | 66.67% | Average Gap Rating | 2.1667
Planned | 1 | 16.67%
Not Implemented | 0 | 0%