## Risk Register
Cybersecurity Risk Register
Organization | HealthData Cloud |  | Methodology | NIST-aligned qualitative scoring |  |  | Scale | 1-5
Risk ID | Domain | Risk Statement | Asset / Process | Likelihood | Impact | Inherent Score | Current Control Strength | Residual Score | Owner | Treatment Plan
R-01 | Identity | Phishing attack leads to compromise of a workforce identity account | Cloud Identity Platform | 5 | 4 | 20 | Weak | 15 | IT Security Lead | Enforce MFA, improve email security, and run phishing simulations
R-02 | Data Protection | Unauthorized privileged access exposes customer data | Customer Database | 4 | 5 | 20 | Moderate | 11 | Head of Engineering | Quarterly access review, privileged monitoring, least-privilege remediation
R-03 | Resilience | Ransomware disrupts endpoint fleet and shared services | Employee Endpoints | 4 | 4 | 16 | Moderate | 9 | IT Operations Manager | Expand EDR coverage, isolate admin rights, and test backup restoration
R-04 | Monitoring | Security logs do not provide timely detection of high-risk activity | Security Monitoring | 3 | 4 | 12 | Weak | 9 | Security Operations Lead | Centralize logs, define alert use cases, and review coverage monthly
R-05 | Third-Party | Critical vendor outage disrupts customer-facing service | Cloud Hosting Provider | 3 | 4 | 12 | Weak | 9 | Vendor Manager | Add resilience clauses, assess failover capabilities, and review continuity annually
R-06 | Compliance | Sensitive data retained beyond justified business need | Data Lifecycle Management | 3 | 3 | 9 | Moderate | 5 | Privacy Manager | Define retention schedule and automate deletion controls
Scoring Guidance | [6 empty] | Risk Summary
Measure | 1 | 2 | 3 | 4 | 5 |  | Metric | Value
Likelihood | Rare | Unlikely | Possible | Likely | Almost Certain |  | Average Inherent Score | 14.8333
Impact | Negligible | Minor | Moderate | Major | Severe |  | Average Residual Score | 9.6667
[7 empty] | Critical / High (Inherent >= 16) | 3
[7 empty] | High Residual (>= 12) | 1

## Heat Map
Risk Heat Map Reference
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
Interpretation | Low | Medium | High | Critical

## Dashboard
Risk Dashboard
Metric | Value | Domain | Residual Score
Total Risks | 6 | Identity | 15
Average Inherent Score | 14.8333 | Data Protection | 11
Average Residual Score | 9.6667 | Resilience | 9
Critical Risks | 3 | Monitoring | 9
High Residual Risks | 1 | Third-Party | 9
|  | Compliance | 5